## Hoja1
OC FOSS Policy - PLAN
Abbreviations
| FOSS Team | team established for setting up and implementing this plan
| FOSS | Free and Open Source Software
| FCO | FOSS Compliance Officer
| OSRB | Open Source Review Board
| FPO | FOSS Project Office | at start, same as OSRB
| FCA | FOSS Compliance Artifacts | generally, Review Report, Licenses, Source Code
| OpenChain | Specification established for ensuring FOSS Compliance
| FOSS Liaison | person designated to deal with outside enquiries | Generallly = FCO
|  | TO DO | DOING | DONE
1 | Situation Analysis
|  |  | Appoint FOSS Project Team | review Project 1 FOSS usage
Analyse Project 1 FOSS usage
review Project 1 contracts
Review Project 1 Processes
request info from SWI
Draft Project Plan
Confirm Project Plan
Draft Situation Report and Recommendation
Share Report and Recommendations with FOSS Team
Carry out OC conformance check
Identify Project 2
2 | Definition of Policy and Procedures
| Policy |  | Draft Policy
Determine Policy Owner and Team
Review FOSS Policy by FOSS Team
Approve FOSS Policy at FOSS Team level
Approve FOSS Policy at Steering level
Store Policy
Define FOSS Contribution Policy
| Procedures |  | Identify FOSS Review Procedures
Define FOSS Identification Procedure
Define FOSS License Collection Procedure
Define FOSS Tracking procedure
Define FOSS obligations Review Procedure
Define FOSS use case and obligations analysis process
Define FOSS source code management process
Define FOSS non-conformity handling process
Define Supply Chain Contract identification, analysis and storage process
Define FOSS Distribution (delivery) compliance process
Define FOSS FCA Archiving process
Define FOSS FCA retrieval process
Define FOSS Contribution process
Define FOSS Policy Review and Update Process
Define FOSS Review Procedure Review and Update Processs
Define FOSS Compliance Audit process
Integrate FOSS Procedures in Quality stream
Review Procedures by FOSS Team
Define FOSS Liaison protocol
Define FOSS Tools manager
| Tools |  | Draft FOSS Review Templates
Determine FOSS Compliance Tools
Determine FCA Repository
3 | Implementation
| Roles |  | Designate FCO
Designate OSRB
Designate FPO
Designate FOSS Liaison
Set up FOSS Liaison communication channels
Designate FOSS Steering Committee
| Training | Adapt OpenChain curriculum to Company
Plan Team and Staff Training
FCO and FPO Training
Tech and Quality and Legal Staff Training
Train FOSS Liaison
Train Tech Staff on FOSS Compliance Tools
| Procedures | Quality to determine FOSS procedure implementation Plan
Distribute FOSS Procedure Templates
| Tools | Set up FOSS Policy and Documentation repository
Set up FCA repository
Set up FOSS compliance Tools
4 | Communication
Determine Communication Content
Detemermine Communication Channel
Communicate FOSS Policy to Company
Communicate FOSS Policy external
5 | Certification
OpenChain self certification
Notify OpenChain self certification